## Sheet1
| Pascal | Zhong Min | Shen Yi Chai | Miao Wen Jun | He Zhi Ming | Wu Ying Ying | Dominique | Lu Ji Ying
What we need to improve
|  | 10 | [6 empty] | Estimation
---The estimation in the beginning differs a lot with real time. We don’t have a deep understand of the big scope when we start to estimate tasks. And we don’t have some basic knowledge.(PhyreEngine, PS2 VU&GS usage)
---Inaccurate workload estimation
-->
Workload is tend to be underestimated. So we should multiply a number for margins. like *1.2
Need to have more time to understand the project scope, and the research the project code during the pre-production period.
|  | 15 | [6 empty] | Code design
---Code structure is bad, at the end we even can’t understand ourselves’ code.(e.g. PhyreScene::Render)
---As a porting project, some mechanisms that changes the original way can cause big issues.(Shadow, VFX sorting, Character Animation)
---We did not do well in getting coders that maintain a certain feature in the code in one game to periodically merge the code to the other game.
---No consideration for code and game system, No code refactor
---No design for new features
---Some code by junior might break the system structure, which can’t be found at once by code review
---Feature's re-factor.
Because many features were started when we only know little of it. So we can't have a perfect framework. So when we found problems of the existing issue, we always tried to use hard-code or trick to solve issue. But we don't tried to re-factor the feature because this action takes a lot of time.
It's better to add some re-factor tasks for some referred stories to finish the re-factor step by step. To keep the coding quality and the working efficiency.
---Lack of research on middleware usage:
We spent 1 man/month to solve each middleware problem:
FMV memory/format/GPU crash/audio crash/thread safety
COLLADA export compatibility
PhyreEngine bugs (gpu fence, audio thread issue, PSV feature implementation)
Shader deserialize corruption (parameter buffer)
FMOD behaviors.
Found the good solution to a problem too late (render-order issue)
--->
Plan more research on middleware at the beginning of project.
Try more products, and prefer AAA title proven middleware, with good support.
Prefer programmers, who are best experienced with 3rd party library programming, to work on middleware.
---No one cares performance when writing code
-->
Need people to care for performance during the whole project, not just only for several sprints
|  | 5 | [6 empty] | Task assignment
---Module owner.
Some modules haven’t owners. Everyone can modify the code as he/she wants even he/she know little of this module. This makes the module is hard to be maintained and can cause new issues for the stories which have been finished.
Every module should have one or more owner. If other guys have any issue with this module, let those guys know. And all the modification should let the module owner(s) know.
Some modules’ owner are not clear (VFX, magic file loading, video, cluster management, etc):
Some modules are managed by different programmers from different teams in different develop stages.
The later maintenance is difficult to continue, because no one knows the initial design concept.
Most bugs from these module are caused by design conflict.
-->
Consider more when tasks are balanced.
Taking long term consistency into account, some teams are not suitable to handle unfinished/emergency tasks from other teams.
|  | 5 | [6 empty] | Hardcode
---We did not find the balance point between hard code and restoring code logic. A lot of hard code was removed and therefore wasted later in the project.
---Hardcode too early, when we find the best solution, we need to rollback these hardcode, and it wastes time.
---Also there’re too many hardcode, some junior guys can just hardcode without consideration, although there is a better way to solve problems globally.
---No unified method to manage all hard code. Some hard code are dangerously redundant because the scope of them is a bit different.
---Code Quality : rapidly the code become a mess, and lot of people hardcoded to fix bugs. As time pass almost all the coder give up to try to make clean code, and hardcoded their patch, making the code more and more messy.
|  | 5 | [6 empty] | Task review
---Code review and commit comment still needs improvement. Sometimes we even loose the condition of a user story can pass or not. But later we still need to fix those bugs left.
---We kind of lost control of code quality during tense period of the project.
---Need to improve code review
---Variable initialization
---Return value
---Forget Delete point for New operation
---...
---Code review didn’t working throughout the team.
This policy is compromised outside shanghai studio and in the period when start releasing members.
How to:
Do it till the end.
---Not follow the coding rules (code review by senior or leader, TDD for new features, interfaces naming...).
At the begin of project, most team can follow coding rules. But when there are too much stories for every team, many team can't follow those rules well. This leads the low code quality and some small coding bugs which let project has more bugs at the later stage.
I think we can let everybody know those rules clearly(like give simple training), and all team leaders must follow those rules.
|  | 10 | [6 empty] | Communication
---Sometimes information is not shared very well among the whole project. e.g. You take a lot of time to fix a bug and find someone already knows about it.
---Very bad communication with Chengdu team, and they don’t have a good management after the leader left.
---We did not have an effective method to monitor Chengdu team code and manage risks. Without face-to-face communication, we failed to control risks during feature implementation, which left a lot of mistakes found later in the debugging stage.
---Work between some team members in one team has little relations, even in the long term.
---The communication between the different cities' developing team, different department and teammates in the same team is not very good.
|  | 5 | [6 empty] | Knowledge Sharing
---Nearly no document, or they’re very early version, probably out of date. So sometimes you need to ask several persons to know who really understands a certain feature.
---Knowledge Sharing: we spend lot of time to redo task that have been made by others peoples.
|  | ? | [6 empty] | Hardware
---Lacks of hardware, PSVita, PS2, PS3, and HD monitor.
Bug
---Sometimes translation of bugs are not good, or even have mistakes.
---We fixed a lot of bugs that could be waived. And those may cause other serious issues later.
---Some bugs can have not only one solution,(e.g. graphic issues that same with PS2, QA just say it looks bad) and we may fail to fix if client is not satisfied with the solution we choose.
---Bug assignment is not good balanced, when someone becomes too busy, others need to fix his bugs they are not familiar with.
---Lack of massive test:
Some aging bugs are reported as 1/1, which can be 1/100 or 100/100, making no difference on threat/fix priority.
-->
Consider some commercial QA service to help at emergency.
Programmers don't know about the overall framework of the project (UI team doesn't know about the multilanguage tasks as the beginning)
-->
Improve Hansoft to have task relationships/ Document shared among the team
|  | 2 | [6 empty] | Comments on the tasks from the TD as techinical reminders
|  | 2 | [6 empty] | Artist
---Data errors(sometimes caused by artists) can ruin the whole build, and it may take a lot of time to fix.(e.g. Rebuild the whole version)
---Artists don’t care the art bugs in game. They always want programmer to told them what’s wrong in MAYA. It seems they just want finish the tasks which they have, but they don’t take care of the whole project.
|  | 20 | [6 empty] | Resource
---Too few seniors and not equally distributed across teams. Team leaders have to spend a majority of time on helping team members finishing user stories, sometimes at the expense of their own.
---Experienced programmers weren’t balanced among teams, then some teams were all very junior programmers
---Team experience is not enough for FF, more senior programmers were needed
---No enough resource, team members are always under stress and lost passion on project.
For this kind of projects, we need more budget on human resource, hardware equipment and schedule. But in fact, we are lack of experienced member who can lead the technique work.
Our machine didn’t get upgraded until the beta period.
And in the earlier stage of project, we were using scrum to manage the project. But the schedule is too tight for scrum. Thus we had to do lots of overtime from the beginning of project.
How to:
More budgets and a realistic schedule for this kind of project.
---We don’t have enough QA to cover the stability.
First we are lack of member in Shanghai team. And XA team is just established and full of fresh member.
Then, we ask QA to do lots of other things than stability test. In which some are helpful to development, but in statistic some costs more than gain.
These make us in a compromised situation in front of client.
How to:
Human resource should be managed more wisely. Something in project cannot be sacrificed.
---The project is too difficulty.
New comer is very hard to do something in this project.
|  | 5 | [6 empty] | Scrum
---Scrum Planning Meeting need to be improved.
---The estimated points were not precise
---Scrum Planning Meeting last too long time
---Scrum costs lots of time and effort. Also it was always out of capability.
---Although scrum ensures us a demo to deliver, we spend lots of time and effort on running it.
Also, there were lots of problems on running scrum. Such as the problem on breakdown user story; the task points were always way higher than proper velocity; the velocity itself was not accurate for us to use, etc.
In the end, programmers just like gave up the scrum and focus on their work, because there were too many for them.
How to:
If we choose to use scrum, make sure to adopt it much more smoothly.
A new method shouldn’t costs more than benefit.
---Story's estimation is too different from the real time we used to finish 1 story.
---Many stories are missing in the backlog.
|  | 2 | [6 empty] | Priority
---To work on user stories by priority. Some user stories are hard and big, but with higher priority, but some teams did small and easy user stories firstly.
Stability
---Dev team didn’t focus on stability.
Deliver build
---Deliver build to client costs too much.
In order to decrease delivery time, we established a build machine directly on client’s studio. Thus we can generate builds on their office.
Although this sounds good and do us a lot of favors, but in order to keep the build identical we have to do lots of works and it didn’t work well.
For the first issue is the unstable VPN network. We’ve met a lot of time that the client’s machine was offline at midnight, even in the middle of building. That created lots of data loss and it’s difficult to debug for them.
Second, we have to keep the machine works just the same as ours, including all environment and workspaces. Thus, any modification on our machine should be synchronized to client machine. And this has to be manually managed and not easy to debug.
How to:
Sometimes, tradition ways are much safer.
If client machine is insisted to be setting up, we need to try our best to secure the network stability.
|  | 2 | [6 empty] | Internal network in studio
---P4 broke down, lost IP address on kit, interesting security policy on our machine…
How to:
What we can do is only contact IT department when something is awfully wrong.
|  | ? | [6 empty] | Data size
---No planning on data size and caused us lots of time in the end.
Game data was always exceeded. And it made us unprepared in most cases.
Also, that caused us using different way on building FFX-2 PS3 and PSVita build.
How to:
We need to create a budget list for data size and prepare some solution in advance.
Data pipeline
---Data rebuild costs too much time and always in high risk.
Although we got all data pipeline on build machine, when we need to rebuild, it scares everyone.
Because it costs a whole night, sometimes one more day to finish it. Also, it will submit almost everything to P4 server, which cause server down frequently. And it also cause the
And the export pipeline didn’t work perfectly. Sometimes it just changes the date in file, then submit it. If we can design it more intelligently, we can save more time.
How to:
Not only consider achieving the full rebuild function, but also paying attention to the released data.
|  | 2 | [6 empty] | Working atmosphere
---Team's working atmosphere was bad because the long time OT working and some guys' left. And because there are too many tasks need to be finished for every team. All teams don't pursuit of quality. There were a lot quarrels which effected people's working positivity.
---No passion for this game.
---Too much overtime work
|  | 10 | [6 empty] | Tasks balance
---Tasks work load balance across teams:
FFX-2 team have extra features to implement with fewer team members (5 people ) to use.
This brings:
no code review
poor coding style(much hardcode against generic problems)
difficult to maintain (no one want to merge code)
lack of debug feature(no accurate level jump, thus no one want to debug on FFX-2/Last Mission, or spent 0.5 hour to go through first)
-->
Consider more when tasks are balanced, taking team member’s capacity into account.
Total | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
What is good
|  | 20 | [6 empty] | Working atmosphere
---The atmosphere is very good
---Good team morale
---The whole team was united
---The whole team was brave to face this big challenge
---The whole team worked very hard to achieve this project
---Hard working and positive attitude.
---Team members had a relatively high morale despite rise and fall.
|  | 10 | [6 empty] | In-team QA
---In-team QA is helpful
---In-team QA freed coders from reproducing difficult bugs, also helped communication between the two teams.
Virtuos QA
---Full PS2 save data
---Full go through video provided by QA
---Useful debug info on bug report(coredump + TTY + savedata)
---Setup test machine and appointed dedicated QA to reproduce unique bugs
Client QA
|  | 5 | [6 empty] | Client programmer
---Client programmer is helpful.
---The client responses very fast, and solved many problems for us.
Powerful debug menu/cheat code
|  | 5 | [6 empty] | Enough PS3 kits
|  | 5 | [6 empty] | Good release stability every day
|  | 5 | [6 empty] | Artists can preview assets locally (SceneViewer, InGameViewer), not just wait for build publishing to see if it’s corrupted.
TA’s help for deep customization on tools (based on latest naming rules, data format requiements, etc)
|  | 5 | [6 empty] | Good IT support on build machine ( providing SSD and RAMDisk), making data build fast.
|  | 10 | [6 empty] | Scrum
---Sprint management is good in this project. The sprint estimation and tasks splitting is helpful to clarify the tasks, and help to find the solution to a problem with a team's efforts
---Demo day (People like it, pity we didn't have it after the first a few sprints)
---Defined clear and systematic user stories
---Organized Release Planning meeting on time
---Assigned user stories of Sprint Backlog to teams, instead let teams to choose freely
---Morning meeting is very helpful
---Scrum helps new team members learn project basics.
---Scrum method(the card playing in sprint meeting) is good for task estimation.
---Good self-mangement
To finish every sprint’s goal, all team members do OT at the begin of project without force. And if there is issue, will report it and let leader or TD or PO know ASAP.
---Finish story with high quality
Through we can’t finish all the stories in most sprints, but all the stories we finished with good quality. This saves a lot of time at the later stage of project. Finishing story with good quality needs good scrum master.
|  | 5 | [6 empty] | Task assignment
---Good Separation of the Task between CD and SH: as we were mostly working on Magic file , our task were really independent off SH work, reducing a lot the merging time.
---Reasonable task assignment.
---Most modules have specific programmer in responsibility, and you can always find the person for help.
---Clean dependency among modules(cloth, postprocess, fios, menu, etc)
Few change after workload estimated for most tasks.
|  | 10 | [6 empty] | Code review
Our team always do the code review (by leader or senior), and avoid some small mistakes.
Code review is good, can reduce the opportunity of new problems happen.
|  | 10 | [6 empty] | Communication
---Good communication in team, people can share solutions in morning meeting, thus reduces redundant work and improves efficiency.
---Good communication and teamwork
Communication is very good in team. Good teamwork to finish every sprint’s goal, help each other during the whole project.
Optimization
---We started optimizations earlier than usual, and worked on it throughout the project.
|  | 5 | [6 empty] | Bug
---Bug is dispatched properly, people work on their familiar area.
---Many bugs can be waived, like ps2 bugs.
We keeps a fast pace from the beginning.
|  | 5 | [6 empty] | Daily Build
---We have daily build for QA to check every day and keeps the game stable.
---All building process has been inducted into CI system, including all data exporting
Although we were modifying the pipeline all the time, it’s been well managed.
---We’ve created a build machine in XA studio and deliver builds directly to XA QA team.
---Daily build is secured throughout the project
Technical/Code:
---Better code maintenance (hg middleware, less branches)
---Good interface design across C and CPP, multi platforms
---Memory corrupt detection on global memory, regardless of data structures. (Better than some previous projects, with only data breakpoints)
---Flexible async load pipeline (handling PS2 and PS3 data, with different sync requirements)
---A single person/owner for each important module (Cloth/Shadow/ATEL/Save), less likely to mess up the code across multiple teams.
Total | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0